## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the proces and include a detailed description of every step. Add reasoning on why you took certain descisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description
Reading and understanding test | 1.5 | 2021-06-15 | Going through the assignment several times to understand completely. Taking a look at assets and design & workflow, planning
Doc reading to refresh memory | 1 | 2021-06-16 | Reading, watching videos about tools I'll need for the test. I.e. recyclerview, Get request, design…
Setup Bitbucket account & project | 1 | 2021-06-17 | Creating account, generating SSH-key, create repo, create Android Studio project
Retrofit | 4 | 2021-06-18 | Setting up Retrofit in project to retrieve data from source. Reading about passing access-key in request, revisiting old projects. Writing ViewModel, first trying to get response into console, googling a lot
RecyclerView | 3 | 2021-06-19 | Creating basic design recyclerview to load data into recyclerview, writing adapters, fixing stuff
Populating RecyclerView | 2 | 2021-06-20 | Manage to load the data to the screen without the images
Glide | 1 | 2021-06-21 | Using Glide to load images into recyclerView, figuring out how to do it from a realtive path and with authorization
Activities & fragments | 3 | 2021-06-21 | Writing the code for the fragments, fixing stuff. Decided to go with single activity, multiple fragments, created bottom navegation view
Design | 2 | 2021-06-21 | Worked a bit on design. Created cardviews for the houses, did the information screen
Structure | 2 | 2021-06-22 | Added search bar, created rough design of house detail view, added more data to views,
Navigation | 2 | 2021-06-22 | Added navigation from cardview to house detail passing data through safeArgs to show on detailed view
Google maps implementation | 2 | 2021-06-23 | Worked on implementing Google maps to the detail fragment. Tapping sends to Maps app and permissions are asked. Tried various things, finally did it adding a fragment to the layout and implenting the code. Had quite some bugs, took some time.
Search feature in recyclerview | 2 | 2021-06-23 | Looking up how to search in the recyclerview. Haven't come up with anything yet.
General | 1 | 2021-06-23 | Worked a bit on design. Cleaned up some code.
Maps | 4 | 2021-06-24 | Continue with Google maps implementation. Creating marker of house in map fragment using coordinates from data.
UI & maps | 5 | 2021-06-25 | Figuring out a way to calculate distance between house and user. Getting user last location , calcullating, displaying it. Cleaned up some code, formatted price to look pretty, hide bottomNavView from detail fragment only, able to get current user location and ask permissions when entering app
Detail Fragment | 4 | 2021-06-26 | Working on displaying distance in detail fragment, fixing bugs due to permissions
Search feature in recyclerview | 3 | 2021-06-27 | Looking up, trying out some some stuff to implement the search feature
Splash screen & search feature | 4 | 2021-06-28 | Looking up, trying out some some stuff to implement the search feature, added splash screen when entering app
Design & search feature | 4 | 2021-06-29 | More on search feature & finalizing design
Search feature | 4 | 2021-06-30 | Found a way to filter results, it was more simple than I thought. Was actually using the wrong elements in XML code. Then added Filterable class and an onTextChanged to the TextInputEditText
Design & last look | 3 | 2021-07-01 | More design, using correct fonts, sizes, color, numbers formatted correctly, finalizing project
Total amount of hours | 58.5